## 1. CURRENT PROJECTS
CONCUR GLOBAL MARKETING - RUNNING PROJECTS
S.NO | PROJECT NAME | PROJECT DESCRIPTION | END USER/CONSUMER | TYPE OF PROJECT | TASKS | SUB TASKS | END DATE | PRIORITY | Visualization | STATUS | COMMENTS
1 | Expense Index - 17Q2 Refresh | Develop a program that can act as an index or benchmark of economic activity | - Storylines (Newsroom articles) | RECURRING | Refresh Expense Index with 17'Q2 data | 1) Base table preparation (17Q2 Expense Data) 2) Perform outlier logic to remove the companies in test/ramp up/ramp down phases 3) Append the data with 17Q1 previous data and refresh the analysis 4) Prepared QoQ, YoY views for all the metrics at overall, industry, segment 5) Create buckets for ramp up and ramp down companies | 2017-07-21 |  |  | Completed
1 | Late Night Dining Analysis | Concur wants to analyse the late night dining expenses to find how the business is growing in top cities and generate scope for improving the travellers experience with vendors via app suggestions and partnerships. | - Storylines (Newsroom articles) | Strategic | 1. Base Table Preparation | 1.1. Build Expense base table to extract dining line items (date range: 2015Q1-2017Q2) | 2017-07-28 | P2 |  | In Progress
1.2. Pull OCR line items corresponding to the dining expense entries
1.3. Prepare the final base table with the Expense Lines and OCR data
[5 empty] | 2. API Development | 2.1. Build Python API to extract the transaction time from expense receipts | 2017-08-11
2.2. Accuracy check: Perform random sample testing to validate API results vs. OCR text
2.3. Improve the accuracy of API extraction by feeding the missing patterns if any
[5 empty] | 3. Data Extraction using API | 3.1. Run python API on 4M OCR receipts data to extract timestamp | 2017-08-14
3.2. Create a consolidated table for 4M receipts are share it with John
2 | Last Minute Travel - Canada/ Global (Significant Markets only) | Concur PR teams wants to release an article around the impact of last minute air bookings in Canada and other top country routes. That helps in suggesting/recommending the better ways for the clients/ travellers in airline bookings for the eleventh hour journeys. | - Concur PR teams | Strategic | 1. Data Preparation | 1.1. Itinerary Global - Airlines base data preparation (Date Range: 2014-17Q2) | 2017-08-21 | P1 |  | Completed | - Will release Canada last minute travel data by Aug 29th, for other significant markets by Sep 6th (Wednesday)!
1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data
[5 empty] | 2. EDA | 2.1. Identify top 10 countries/regions based on yearly air tickets volume and amount spend | 2017-08-22
[5 empty] | 3. Determine Trip Characteristics | 3.1. Classify the trip as one way/ round trip and flight as domestic/ international | 2017-08-25
3.2. Filter the data set only for top 1000/ major portion of the routes in country/ region
[5 empty] | 4. Country/ Regional Level Air Data (Canada,US,UK,Germany,Australia and France) | 4.1. Booking behaviour of business travellers by yearly trend | 2017-09-04
4.2. Average airfare by booking window (0-3, 4-7, 8-14, 15+ days)
4.3. Average airfare by month for the booking windows - 7 OR FEWER, 8 OR MORE days
4.4. %Difference in airfare between booking windows (<=7 & >=8) by month
4.5. User age band analysis by booking window (0-3, 4-7, 8-14, 15+ days)
4.6. Class of service analysis by booking window (0-3, 4-7, 8-14, 15+ days)
4.7. Top air vendor analysis by booking window (0-3, 4-7, 8-14, 15+ days)
[5 empty] | Industry Cut (Air Tickets & Spend) | 5.1. Booking behaviour of business travellers by yearly trend | 2017-07-11
5.2. Average airfare by booking window (0-3, 4-7, 8-14, 15+ days)
5.3. Average airfare by month for the booking windows - 7 OR FEWER, 8 OR MORE days
5.4. %Difference in airfare between booking windows (<=7 & >=8) by month
5.5. User age band analysis by booking window (0-3, 4-7, 8-14, 15+ days)
5.6. Class of service analysis by booking window (0-3, 4-7, 8-14, 15+ days)
[5 empty] | 5. Testing Metrics Data | 5.1. QC the final country level metrics data | 2017-09-05
[5 empty] | 6. Deployment | 6.1. Sharing final data package | 2017-09-05
3 | Busiest Travel Day Analysis | According to Concur data, Sept-Dec is the busiest time of year for business travel, so it’s a good time for you to assess your risk messaging/duty of care solution to ensure you can guarantee you’ll be able to locate and communicate with an employee should they be in danger and ensure their safety in a timely manner. The key to any successful duty of care is preparation and planning so use this time to assess your duty of care solution and ensure employees know what to expect in the event of an emergency before they hit the road this fall. | - Concur PR teams | Strategic | 1. Data Preparation | 1.1. Itinerary Global - Airlines base data preparation (Date Range: 2016) | 2017-09-08 |  |  | Completed
1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data
[5 empty] | 2. Busiest travel Day/Season (Logic 1& 2) | 2.1. Day/Season with most travelers on trip | 9/13/2017 / (9/20/2017)
2.2. Does it vary by country/region?
[5 empty] | 3. Location - large vs. small cities , Domestic & International and Frequent and infrequent.(conferences) | 3.1. Top destinations for air travel | 2017-09-22
[6 empty] | 3.2. Investigate the data again for Frequent/Infrequent, as for Infrequent we are seeing almost 99% users, which is highly ambiguous | 2017-09-26
3.3. Complete Domestic v/s International User Distribution for each country for "Time Duration/In between Days" Logic
[6 empty] | 3.4. Complete Top routes for both Domestic and International for "Time Duration/In Between Days" Logic for all the countries | 2017-09-29
[6 empty] | 3.5. Complete Small City/Large City for "Start Date" Logic | 2017-10-03
[6 empty] | 3.6. Complete Frequent & Infrequent for "Start Date" Logic | 2017-10-05
[6 empty] | 3.7. Complete Domestic v/s International and Top routes for both at each country level for "Start Date" Logic | 2017-10-10
[5 empty] | 4. Characteristics of the trip/Kind of people travelling | 4.1. % on same/diff continent | 2017-10-16
4.2. % in major countries that are international?
4.3. Who are the kind of people who travel in this period? (Age Band & Class of service) - Does it vary by country/region?
4 | Fast Fact - 2017Q3 Refresh | Provides global stats of Concur in terms of Companies, Users and Billable transactions | RECURRING | Refresh the dashboard with 2017Q3 data | Add 2017Q3 billable transactions, expenses and trips data from EDW & Hadoop | 1. Identify theglobal level data metrics from hadoop and edw DB 2. Refresh all the data metrics | 2017-10-18 |  |  | Completed
5 | Rise in Rail Travel in EU | Concur Expands Rail Support to Spain, Sweden and Italy as European Rail Travel Continues to Rise | Concur PR team | Strategic | 1. Data Preparation | 1.1. Itinerary Global - Rails base data preparation (Date Range: 2014-17) | 2017-10-23 | P1 |  | Completed
[6 empty] | 1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data | 2017-10-23
[5 empty] | 2. Status of Rail travel | 2.1. # Routes & trips - Global /Country (UK,DE,FR,Sweden, Spain & Italy)level (YoY & MoM) | 2017-10-25 |  | Bar Chart
[6 empty] | 2.2. # of Bookings, # Travellers over the period of time - Global /Country (UK,DE,FR,Sweden, Spain & Italy)level (YoY & MoM) | 2017-10-27 |  | Bar Chart
[6 empty] | 2.3. New routes over the time period | 2017-11-02 |  | Line Graph
[6 empty] | 2.4. Domestic/International routes (Top 10 Routes: global & country level) - Bookings, Trips, Travellers | 2017-11-06 |  | Pie Chart/Bar chart
[6 empty] | 2.5. Seasonal routes top 10 |  |  | Line Graph
[6 empty] | 2.6 Tier1 cities vs other cities (Top 5 cities based on Population/Trips) | 2017-11-08
[5 empty] | 3. Data breakdown at Different level | 3.1. Class of service breakdown |  |  | Pie chart
[6 empty] | 3.2. Type of travellers - Age band | 2017-11-10 |  | Line Graph
[6 empty] | 3.3. Vendor Analysis |  |  | Pie chart
[6 empty] | 3.4. Offline booking vs Online booking (lag b/w travel date and booking date) | 2017-11-14 |  | Line Graph
[5 empty] | 5. Testing Metrics Data | 5.1. QC the final country level metrics data
[5 empty] | 6. Deployment | 6.1. Sharing final data package
6 | Busiest Expense Day | If you work in finance, the end of the year is probably your busiest time of year because of the end of the year crunch for employees to get their expense reports in so you can close the books on the year. Our data supports this with an increased volume of expense reports being submitted with an increased amount expensed. | Concur PR team | Strategic | 1. Data Preparation | 1.1. Expense base data preparation | 2017-11-10 | P1 |  | Completed
1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data
[5 empty] | 2. Time Period for busiest expense reporting number (PHASE 1) | 2.1. Busiest expense day (w.r.t. other peak points across the year, Last 5 years) Global & Country level | 2017-11-14 |  | Line Graph
[6 empty] | 2.2. Spikes in types of expenses: gifts, entertainment (holiday parties), team outings | 2017-11-15 |  | Stack bar
[5 empty] | 3. Different data cuts (PHASE 2) | 3.1. Mobile use vs. desktop for submitting | 2017-11-20 |  | Bar Chart
[6 empty] | 3.2. Industry level customers peaks at different times during the year |  |  | Pie Chart
[5 empty] | 4. Testing Metrics Data | 4.1. QC the final country level metrics data | 2017-11-22
[5 empty] | 5. Deployment | 5.1. Sharing final data package
[5 empty] | 6. Aditional Requests | 6.1. Workflow times: Avg lsg between submission of reports from transactions | 2017-11-30
6.2. Hourly distribution of report submission in businest expense day
6.3. Mobile Explorations: Google Analytics and Mobile Actions data
6.4. Mobile Receipts Upload on busiest expense day
7 | Expense Index - 2017Q3 (2015Q1-2017Q1) | Develop a program that can act as an index or benchmark of economic activity | Concur PR team | STRATEGIC/ RECURRING | 1. Data Preparation | 1.1. Expense base data preparation (2015Q1-2017Q1 Data) | 2017-12-12 | P1 |  | In Progress
1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data
[5 empty] | 2. Overall Index Company growth | 2.1. YoY growth based on spend | 12/19/2017 |  | Bar Chart
[6 empty] | 2.2. Segments (Ent vs. SMN) |  |  | Line Graph |  | Re-run the index seprately by SMN and ENT
[6 empty] | 2.3. Geo (Reporting country vs. Expense country) |  |  | Bar Chart
[6 empty] | 2.4. Index by spend buckets (<1M, 1-10M, 10-100M, 100-500M, >500M) |  |  | Line Graph
[6 empty] | 2.5. Industry |  |  | Line Graph |  | Waiting for this data from SAP
[5 empty] | 5. Testing Metrics Data | 4.1. QC the final country level metrics data
[5 empty] | 6. Deployment | 5.1. Sharing final data package
8 | Expense Index - 2017Q3 (2015Q4-2017Q3) | Develop a program that can act as an index or benchmark of economic activity | Concur PR team | STRATEGIC/ RECURRING | 1. Data Preparation | 1.1. Expense base data preparation (2015Q4-17Q3) | 2017-12-12 | P1 |  | In Progress
1.2. Outlier treatment: Process of detecting, diagnosing, and editing faulty data
[5 empty] | 2. Overall Index Company growth | 2.1. YoY growth based on spend | 2017-12-19 |  | Bar Chart
[6 empty] | 2.2. Segments (Ent vs. SMN) |  |  | Line Graph |  | Re-run the index seprately by SMN and ENT
[6 empty] | 2.3. Geo (Reporting country vs. Expense country) |  |  | Bar Chart
[6 empty] | 2.4. Index by spend buckets (<1M, 1-10M, 10-100M, 100-500M, >500M) |  |  | Line Graph
[6 empty] | 2.5. Industry |  |  | Line Graph |  | Waiting for this data from SAP
[5 empty] | 5. Testing Metrics Data | 4.1. QC the final country level metrics data
[5 empty] | 6. Deployment | 5.1. Sharing final data package
9 | Late Night Dining Analysis (Revisit) | Concur wants to analyse the late night dining expenses to find how the business is growing in top cities and generate scope for improving the travellers experience with vendors via app suggestions and partnerships. | - Storylines (Newsroom articles) | Strategic | 1. Base Table Preparation | 1.1. Build Expense base table to extract dining line items (date range: 2015Q1-2017Q3) | 2017-12-28 |  |  | TBD
1.2. Pull OCR line items corresponding to the dining expense entries
1.3. Prepare the final base table with the Expense Lines and OCR data
[5 empty] | 2. API Development | 2.1. Build Python API to extract the transaction time from expense receipts | 2018-01-12
2.2. Accuracy check: Perform random sample testing to validate API results vs. OCR text
2.3. Improve the accuracy of API extraction by feeding the missing patterns if any
[5 empty] | 3. Data Extraction using API | 3.1. Run python API on Dining OCR receipts data to extract timestamp
3.2. Run python API for OCR receipts to extract time stamp
[5 empty] | 4. Data Cleaning | 4.1. Outlier Detection: Identify and remove the data anomalies | 2018-01-26
[5 empty] | 5. Business Analysis | 5.1. Dining traffic distribution at different hours of the day (0-2AM, 2-4AM, 4-6AM..) |  |  | Line Graph
[6 empty] | 5.2. Share of late night meals in overall dining expenses |  |  | Pie Chart
[6 empty] | 5.3. Growth of late night dining over the time(QoQ, YoY trends) |  |  | Bar Chart
[6 empty] | 5.4. Most used vendors and apps for late night dining (Emerging restaurants) |  |  | Pie Chart
5.5. Companies which are spending a lot in late night dining
5.6. Average cost of meal types (Breakfast, Lunch, Dinner, Meal) vs. Late night meals
[6 empty] | 5.7. Travelers behaviour by generations - Overall, App and Vendors |  |  | Line chart
[5 empty] | 6. Testing Metric Values | 6.1. Validate all the metrics data
[5 empty] | 7. Deployment | 7.1. Sharing final deliverable as a package
10 | Last Minute Hotel Bookings | Analyse the hotel booking experience of a business traveller at eleventh hour (last minute). That helps in identifying, the cost variance of a hotel in different booking windows. Analyse the most used partnered vendors(Hotel Tonight) behaviour for last minute hotel bookings. | - Storylines (Newsroom articles) | Strategic | 1. Data Preparation | 1.1. Itinerary base table preparation (Hotel): 2015-17 |  |  |  | TBD
1.2. Create different booking windows (<1, 1-3, 4-7, 8-14, 15+ days)
[5 empty] | 2. Data Cleansing | 2.1. Identify the abnormal hotel transactions at company and end user levels
[5 empty] | 3. Business Analysis | 3.1. Average cost of hotel by different booking windows
3.2. Last minute hotel cost from different hotel vendors and Hotel Tonight
3.3. Cost variance analysis: Top 10 hotel vendors vs. other vendors
3.4. Average cost of a last minute hotel booking in top 20 cities
3.5. Last minute hotel bookings by traveller generations (Booking window vs. Traveller Age)
3.6. Best practices for the clients to save cost in last minute hotel bookings
[5 empty] | 4. Testing Metric Values | 4.1. Validate all metrics data against calculations and logics
[5 empty] | 5. Deployment | 5.1. Sharing the final deliverable
11 | International Rideshare Analysis | Concur wants to analyse the top rideshare vendors usage in different countries by the business travellers coming from outside the country/regions. That helps in measuring the average cost per ride to set the proxies for reimbursements! | - Storylines (Newsroom articles) | Strategic | 1. Data Preparation | 1.1. Expense base table preparation for Rideshares: 2015-17 (Reimbursement currency for home) |  |  |  | TBD
1.2. Build RegEx to capture vendors and rideshare expenses
[5 empty] | 2. Data Cleansing | 2.1. Remove the suspicious transactions from the data
[5 empty] | 3. Business Analysis | 3.1. Rideshare usage for the users who are coming outside of the country
3.2. Most used rideshare vendors in different countries and cities
3.3. Growth of rideshare business and partnered vendors over the time (QoQ, YoY trends)
3.4. Share of rideshare business w.r.t overall ground transportation business
3.5. Average cost of ride for different vendors
3.6. Rideshare vendor usage by different travel generations
3.7. Emerging markets and it's share to target rideshare business
[5 empty] | 4. Testing Metric Values | 4.1. Validate all the metrics data against logics and business definitions
[5 empty] | 5. Deployment | 5.1. Sharing the final deliverable
12 | Vendor Analysis (Not travel data) | Analyse and track the emerging vendors used by business travellers in different expense types. It helps Concur for business partnerships to attract the travellers based out of the locale. These partnerships will decrease cost to the travellers while using these vendors with Concur cap. | - Storylines (Newsroom articles) | Strategic | 1. Data Preparation | 1.1. Expense base table preparation: 2015-17 |  |  |  | TBD
[5 empty] | 2. Data Cleansing | 2.1. Build fuzzy logic to clean the vendor names from User feeds, Card Payment feeds
2.2. Remove the transactional elements with abnormal/suspicious behaviour
[5 empty] | 3. Business Analysis | 3.1. Vendors with tremendous growth over the time (QoQ, YoY)
3.2. Identification of opportunities for vendor partnership program
3.3. Best vendor suggestions for different type of expenses in different countries/cities
3.4. Usage of the existing partnered vendors
3.5. Cost variance in different vendors for the similar expense types
3.6. Vendor preferences for different traveller generations
3.7. Different payment card recommendations to better enhance the expense workflows
[5 empty] | 4. Testing Metric Values | 4.1. Validate all metrics data against business logics and definitions
[5 empty] | 5. Deployment | 5.1. Sharing the final deliverable
13 | Wildcard (Spend Type) Analysis | Track what are most expensing spend categories by companies, industries, segments and in regions. Helps to build the customized recommendation engine to share best vendors/apps/card programs to make the expense flow effortless. | - Storylines (Newsroom articles) | Strategic | 1. Data Preparation | 1.1. Expense Data Preparation: 2015-17 |  |  |  | TBD
1.2. Build RegEx to create proper expense types
[5 empty] | 2. Data Cleansing | 2.1. Remove outliers existing the data based on $amounts
[5 empty] | 3. Business Analysis | 3.1. Most spending categories in different markets, countries, cities, industry and segment
3.2. Track the usage of the expense types in different time buckets (hourly traffic)
3.3. Top 10 vendors mostly used for each of the spend category
3.4. Avg. expense cost on each of the type by different traveller generations
3.5. Payment type (Cash vs. Card) analysis
[5 empty] | 4. Testing Metric Values | 4.1. Validate all metrics data against business logics and definitions
[5 empty] | 5. Deployment | 5.1. Sharing the final deliverable
14 | Late Night Dining - Extension | With in US, Identify the travellers dining options if they are flying to different parts of the country and do they dine in Big Food Chains vs. Regional Food Chains | - Storylines (Newsroom articles) | Strategic | 1. Data Preparation | 1.1. Prepare dining expenses data: 2015-17 |  |  |  | TBD
1.2. Combine Expense and Itinerary to get the start and end country of the travel journey
[5 empty] | 2. Data Cleansing | 2.1. Remove any suspicious line items exist in the data set
[5 empty] | 3. Business Analysis | 3.1. Track the dining options (Big Food vs. Regional) for the travellers with in the market
3.2. Analyse the traveller generations with the food option selections
[5 empty] | 4. Testing Metric Values | 4.1. Validate all metrics data against business logics and definitions
[5 empty] | 5. Deployment | 5.1. Sharing the final deliverable
15 | Market Dashboard: Tableau Developments | Create tableau dashboard to showcase the list of KPIs in Market Dashboards |  | Ad-hoc | 1. Tableau Automation of Market Dashboard | 1.1. Create whiteboards 1.2. Scripts building automation 1.3. Tableau development 1.4. Testing 1.5. Host the dashboard on tableau server |  |  |  | TBD